GarantiFi White Paper: Research & Build Plan

Output: ~30-page white paper → alignment document for the team → source material for the final 6-slide pitch deck.

Working method: One module at a time. Each module = deep research first, then structured writing. You review, correct, add context. We lock it. Then move to the next.

Module 1 — The Problem

Research targets:

Brazil's credit exclusion data: size, who is excluded, why (source: World Bank, BCB — Banco Central do Brasil, IBGE)

Pawn market in Brazil: CAIXA volumes, average LTV, default rates, branch coverage gaps

Consumer credit rates in Brazil vs OECD — the 40–150% APR reality with hard numbers

"Asset-rich, cash-poor" population sizing: luxury goods ownership estimates in Brazil

Informal credit market size and its predatory terms

Comparison: why existing DeFi fails this segment (no physical collateral accepted on any major protocol)

Cross-reference with LatAm and globally: is this problem unique to Brazil or systemic?

Output: 3–4 pages. Problem statement, quantified, evidence-backed, with no assumptions.

Module 2 — Why Now

Research targets:

Solana RWA ecosystem status March–April 2026: TVL, number of protocols, lending deposits, holder count

Brazil crypto adoption current data: user count, volume, stablecoin dominance, regulatory environment (Drex, PIX, BCB sandbox)

Physical collateral on-chain: what protocols exist globally, what gap GarantiFi fills

Global RWA tokenization momentum: BCG/McKinsey/Ripple forecasts, institutional adoption

Regulatory tailwinds in Brazil specifically: SCD license framework, FIDC, CVM tokenization rules

LatAm fintech cycle: why now is the inflection point (post-Nubank, PIX infrastructure, crypto penetration)

Why physical luxury collateral is being created as a category now, not in 2021 or 2019

Output: 3–4 pages. Not generic "crypto is growing" — specific, timed, evidence-backed.

Module 3 — The Product

Research targets:

cNFT / compressed NFT technical implementation on Solana (Metaplex Bubblegum): how custody proof works, what is stored on-chain vs IPFS/Arweave

Triangular appraisal model: how online (R$215) and in-person (R$450) appraisals work, industry standards for luxury goods valuation (Chrono24, WatchBox, GIA for jewelry, FIPE for vehicles)

Vault architecture: how P2P crowdlending pools work on-chain, lender vault mechanics, interest accrual

Liquidity mismatch problem: what happens when a lender wants early exit before loan matures — research best practices: secondary market for vault positions, tranching, liquidity reserves, insurance pools, existing protocols solving this (Maple Finance, Goldfinch, Centrifuge)

Default and recovery mechanics: deep research on:

On-chain auction of physical asset (current plan) — how this works legally, what platforms do this, precedents

NFT fractionalization for ownership transfer — legal and technical feasibility

Full NFT ownership sale — buyer takes physical delivery

Insurance products for RWA default

Recovery rate benchmarks in pawn/asset lending (target >90%)

BRL stablecoin risk: depeg monitoring, dual-vault architecture (USDC + BRL)

Smart contract audit requirements: firms, timeline, cost

Technical risks and mitigants

Output: 5–6 pages. Full product spec including open problems, proposed solutions, and risk matrix.

Module 4 — The Team

Research targets:

Gitel.com.br: company profile, size, markets, security sector scope in Brazil — evidence of operational scale and bank/corporate network

Brazil security sector market: relevance to custody operations, physical asset transport, vault management

Wall Street / Boston finance credentials: what this signals to judges and investors (Colosseum specifically values finance + crypto crossover)

George's profile: Italian banking education system (Bocconi, relevant institutions), CEE banking operations context — what European financial discipline means in a LatAm context

Pattern matching: which winning Colosseum teams had similar compositions (finance + operator + developer)

Why this team is uniquely positioned: no one else has the custody network + banking discipline + on-chain build capacity simultaneously

Output: 2–3 pages. Each person has a concrete role and a concrete credential. Founder-market fit argument is built from evidence, not claims.

Module 5 — Business Model and Moat

Research targets:

P2P lending economics: how crowdlending platforms like Nexo, Credix, Goldfinch, Maple price loans, split yield, manage risk

Revenue model deep-dive: origination, spread, liquidation, rollover, and Layer 2 streams (Kamino yield, VaaS, Asset Scoring API)

Unit economics validation: CLV R$2,865, CAC R$350–500, rollover margin improvement from 16.8% to 26% — stress-test these numbers

Breakeven model: 400 CCBs at R$20K average, 60% rollover — does the math hold?

Year 1 / Year 2 projections: conservative, base, optimistic scenarios

Competitive moat depth: why can't CAIXA, banks, or a well-funded startup replicate this in 18 months?

Network effects: custodian network, appraiser network, borrower on-chain credit history (reputation as moat)

Layer 2 revenue streams: VaaS for third parties, Asset Scoring API, on-chain securitization — size these

LatAm asset-light expansion economics: why R$10–45K per country is credible

US market entry: pawnbroker license requirements in FL and NY, TAM $8.6B → $45.6B by 2030 — verify

Output: 5–6 pages. Bullet-proof, scenario-tested, with explicit moat analysis.

Module 6 — The Ask and Roadmap

Research targets:

Colosseum accelerator: what the $250K actually covers, what they expect at each milestone

Cost structure breakdown: smart contract audit ($30–80K range), legal entity + SCD license (Brazil), custodian network setup, appraiser onboarding, first marketing/acquisition, team runway

Phase-by-phase budget: each milestone with estimated cost and what de-risks it

Seed round sizing after accelerator: what comparable RWA/DeFi seed rounds looked like in 2025–2026

LatAm expansion cost model: per-country playbook economics

US entry cost: pawnbroker licensing timeline and cost in FL/NY, compliance overhead

Comparable valuations: RWA DeFi protocol seed rounds, comparable company multiples

Exit / liquidity scenarios for early investors: token launch, acquisition, Series A

Output: 4–5 pages. Every dollar accounted for, every milestone clearly connected to a risk removed or a value created.

Execution Sequence

| Step | Module | Estimated depth |
| --- | --- | --- |
| 1 | Problem | 3–4 pages, ~2 research rounds |
| 2 | Why Now | 3–4 pages, ~2 research rounds |
| 3 | Product (including liquidity + default research) | 5–6 pages, ~3 research rounds |
| 4 | Team | 2–3 pages, ~1–2 research rounds |
| 5 | Business Model + Moat | 5–6 pages, ~3 research rounds |
| 6 | Ask + Roadmap | 4–5 pages, ~2 research rounds |

At the end of all 6 modules: compile into a single formatted white paper document, then distill into the 6-slide deck.