# Vaulx Backend / On-Chain BRD — for Edson

Owner: Edson (Lead Dev) · Sponsor: George + Marcelo · Date: April 22, 2026
 Target: Colosseum Frontier Hackathon submission, May 10, 2026 (18 days)
 Source of truth: Canonical Spec v3 · Frontend BRD (companion doc)

## 1. Scope

You own, end-to-end:

- All Anchor programs (TRDC, Vault, Loan, Auction)

- The Anchor test suite — including named failing tests that serve as Demo Moment 6

- Off-chain backend: event monitor / indexer, API endpoints powering the frontend's non-chain reads, IPFS gateway proxy, SSE test-runner endpoint

- Devnet deployment + upgrade management

- Demo seed and choreography scripts

You do not own:

- Frontend UI (George + Marcelo + Claude Code Max)

- CCB document generation on the client (frontend handles; you validate the hash)

- UX for any of the roles

The handshake. Frontend consumes your IDLs + events. Frontend needs IDL stability by May 1 (Day 10) so the Week 2 build doesn't thrash on type regens. Anything you change after May 1 requires a frontend sync call same day.

Success = all 9 demo moments executable on Devnet by May 6 (Day 15 — rehearsal day). Moments are enumerated in §7 of the Frontend BRD; the summary is: (1) lender deposit, (2) borrower mint TRDC, (3) custody confirm, (4) disburse via CPI, (5) repay + yield, (6) failing-test demo, (7) renewal, (8) multi-currency vaults, (9) default + auction.

## 2. Deliverables — the 8 things

| # | Deliverable | Notes |
| --- | --- | --- |
| 1 | TRDC Program | cNFT via Bubblegum; 7-state machine; metadata schema frozen |
| 2 | Vault Program | One codebase, 4 vaults via PDA seeds; deposit/withdraw + CPI-only disburse |
| 3 | Loan Program | Lifecycle: create → confirm_custody → disburse CPI → pay / renew / repay / default |
| 4 | Auction Program | Privileged auction on defaulted TRDCs; whitelist + highest bid + 5% protocol fee |
| 5 | Anchor test suite | Full coverage + named failing tests powering Moment 6 |
| 6 | Event monitor / indexer | Watches logs, writes to Supabase, powers frontend state |
| 7 | Demo orchestration scripts | Seed Devnet state, pre-fund wallets, run scripted flows |
| 8 | SSE test-runner endpoint | Streams anchor test output to /admin/tests frontend |

## 3. TRDC Program — the state machine

Representation. TRDC is a compressed NFT via Metaplex Bubblegum. Metadata stored via standard cNFT metadata; state is held in a companion PDA account keyed by the cNFT mint (because cNFT metadata is write-expensive — state lives in a PDA for cheap mutation).

Metadata schema (on the cNFT, written once at mint):

| Field | Type | Notes |
| --- | --- | --- |
| ccb_hash | [u8; 32] | SHA-256 of CCB PDF; frontend computes, you verify on-chain |
| ccb_external_id | String (≤32 bytes) | Human-readable loan ID, e.g. VLX-2026-000123 |
| custodian_id | Pubkey | Authorized custodian wallet |
| borrower | Pubkey |  |
| scd_pubkey | Pubkey | Licensed counterparty (SCD partner) |
| asset_category | u8 (enum) | watch / jewelry / art / vehicle / nft |
| appraisal_value | u64 | In BRL centavos or USDC micros, whichever matches vault currency |
| loan_amount | u64 | Principal |
| ltv_bps | u16 | Loan-to-value in basis points (e.g., 5000 = 50%) |
| rate_bps_per_month | u16 | Monthly rate × 10,000 (220 = 2.2%/mo) |
| origin_ts | i64 | Unix timestamp |
| term_days | u16 | 120 for Phase 0 |
| due_ts | i64 | Updates on renewal |

State PDA (seeds: [b"trdc_state", mint.key().as_ref()]):

pub struct TRDCState {

pub mint: Pubkey,

pub status: TRDCStatus,

pub installments_paid: u8,       // 0..=4 for Phase 0

pub last_payment_ts: i64,

pub renewal_count: u16,

pub amendment_hashes: Vec<[u8; 32]>,  // bounded; max 10 renewals

}

State machine — enforce strictly, no rewinds:

| From → To | Instruction | Signer | Guard |
| --- | --- | --- | --- |
| — → PENDING_CUSTODY | create_ccb_trdc | Borrower | Appraisal median validated; LTV ≤ max |
| PENDING_CUSTODY → ACTIVE | confirm_custody | Custodian (must match custodian_id) | TRDC exists; physical intake recorded |
| ACTIVE → RENEWED → ACTIVE | renew_ccb | Borrower | Within renewal window; amendment hash provided; interest paid current |
| ACTIVE → REPAID | repay_ccb | Borrower | Full outstanding = principal + accrued interest |
| ACTIVE → OVERDUE | mark_overdue | Anyone (permissionless crank) | Past due_ts or missed installment window |
| OVERDUE → DEFAULTED | execute_af_default | 2-of-3 Squads multisig (dev feature flag bypasses for demo) | Grace period expired |
| DEFAULTED → LIQUIDATED | close_auction (from Auction Program) | Auction Program via CPI | Winning bid cleared |

Any other transition attempt → InvalidStateTransition error.

The RENEWED intermediate state. Exists so on-chain observers see a discrete event for the renewal (renewal_count++, amendment_hash appended, due_ts updated). Instruction is atomic: ACTIVE → RENEWED → ACTIVE in a single call.

## 4. Vault Program — one codebase, four deployments

The four vaults. Same program, different PDA seeds + different token mints + different authority configurations. Frontend consumes them as 4 distinct vault accounts.

| Vault | Token mint | Seeds | Notes |
| --- | --- | --- | --- |
| Institutional-USDC | Devnet USDC | [b"vault", USDC_MINT, INST_AUTH] | Phase 0 primary vault |
| Institutional-BRL | Devnet BRZ (or mock) | [b"vault", BRZ_MINT, INST_AUTH] | Demo Moment 8 |
| Retail-FIDC-USDC | Devnet USDC | [b"vault", USDC_MINT, FIDC_AUTH] | Deploy; deposit flow mocked via FIDC wrapper for demo |
| Retail-FIDC-BRL | Devnet BRZ | [b"vault", BRZ_MINT, FIDC_AUTH] | Same pattern |

Core instructions.

- initialize_vault(mint, authority, config) — admin only; creates PDA + shares mint

- deposit(amount) — user transfers tokens in, receives share tokens; KYC gate: require civic_pass_token account (production) / skip in demo via feature flag

- withdraw(shares) — burn shares, transfer proportional tokens out

- disburse(trdc_mint, amount) — CPI-only; NOT callable externally; transfers loan principal from vault ATA to borrower ATA

The custody-gate invariant. This is the line of code that is the whole thesis:

// inside disburse()

require!(

trdc_state.status == TRDCStatus::Active,

VaulxError::CustodyNotConfirmed

);

Placed before any token movement. Enforce at the account-constraint level too via #[account(constraint = trdc_state.status == TRDCStatus::Active @ VaulxError::CustodyNotConfirmed)] on the accounts struct — belt and suspenders.

The CPI-caller enforcement. disburse must reject direct external calls. Two layers:

- Require authority signer to be the Loan Program's PDA (derive: [b"loan_authority"] from Loan Program ID). Use Signer<'info> + check that the signer's pubkey matches the expected PDA.

- Inspect the instruction sysvar: verify the current instruction was invoked as a CPI (outermost instruction's program_id != Vault Program ID). Return UnauthorizedCaller if direct.

Share accounting. Standard vault shares — shares_out = amount * total_shares / total_underlying on deposit, inverse on withdraw. Handle the zero-shares edge case (first depositor gets shares = amount). Use checked_mul / checked_div everywhere; overflow → error, not panic.

## 5. Loan Program — lifecycle orchestrator

This is the program the frontend calls for every borrower action. Internally it CPIs into Vault (for disburse) and TRDC (for state transitions).

Instructions:

| Instruction | Signer | What it does |
| --- | --- | --- |
| create_ccb_trdc(ccb_hash, external_id, custodian_id, asset_category, appraisal_value, loan_amount, ltv_bps, rate_bps_per_month, term_days, scd_pubkey) | Borrower | Mints cNFT via Bubblegum CPI; creates TRDCState PDA with status = PENDING_CUSTODY; validates LTV, min ticket, rate bounds |
| confirm_custody(trdc_mint) | Custodian | Transitions TRDCState → ACTIVE; immediately CPIs vault.disburse() in the same instruction — atomic. If disburse fails, whole transaction reverts. |
| pay_installment(trdc_mint, amount) | Borrower | Validates amount == expected monthly interest; transfers to vault ATA; increments installments_paid; updates last_payment_ts |
| renew_ccb(trdc_mint, amendment_hash, new_due_ts) | Borrower | Validates within renewal window; requires current interest paid; appends amendment_hash; transitions ACTIVE → RENEWED → ACTIVE atomically; updates due_ts; increments renewal_count |
| repay_ccb(trdc_mint) | Borrower | Computes final settlement (principal + accrued interest + any late fees); transfers to vault ATA via user token account; state → REPAID |
| mark_overdue(trdc_mint) | Permissionless crank | Checks due_ts or installment deadlines vs. current clock; transitions to OVERDUE if past grace |
| execute_af_default(trdc_mint) | 2-of-3 Squads multisig (bypass flag for demo) | Transitions OVERDUE → DEFAULTED; creates Auction PDA via CPI to Auction Program |

Interest accrual model. Monthly simple: interest_per_installment = principal × rate_bps_per_month / 10_000. Four installments per 120-day Phase 0 cycle. Accrued-but-unpaid interest accumulates if an installment is late. Late fee: flat R$150 equivalent per overdue installment (configurable constant).

Atomicity. confirm_custody → disburse is one transaction. Any failure (vault balance insufficient, KYC missing on borrower, sysvar-check fails) reverts everything. This is critical: if disburse fails silently while state flips to ACTIVE, we have a borrower with an active loan and no funds. Don't let this happen.

## 6. Auction Program — Moment 9

Purpose. When a TRDC defaults, a privileged auction opens. Whitelisted lenders (institutional + long-hold retail) bid first; if no bid clears, public market opens 72h later. Winning bid sends proceeds back to the originating vault minus a 5% protocol fee.

Scope for hackathon: minimum viable. Don't over-engineer.

Accounts.

- Auction PDA (seeds: [b"auction", trdc_mint.as_ref()]) containing: trdc_mint, opening_price (M3 market anchor value), current_highest_bid, current_highest_bidder, whitelist_window_end, public_window_end, status

- Whitelist PDA (global, admin-managed for demo) — simple pubkey set

Instructions.

- create_auction(trdc_mint, opening_price) — CPI-only from Loan Program's execute_af_default

- place_bid(auction, amount) — must be > current highest; whitelist check if within whitelist window; transfers bid amount into escrow

- close_auction(auction) — permissionless after window closes; returns proceeds to vault, 5% fee to treasury, transitions TRDC → LIQUIDATED, refunds losing bidders

Demo shortcut: whitelist window of 60 seconds (vs. 72h production). Admin feature flag forces timestamp-skip for demo recording.

## 7. Test suite — the demo-critical part

The tests that must exist with these exact names (the /admin/tests frontend screen parses them by name):

| Test | Expected outcome | Purpose |
| --- | --- | --- |
| test_disburse_fails_when_custody_not_confirmed | FAIL with CustodyNotConfirmed | The main Moment 6 artifact |
| test_disburse_fails_with_unauthorized_caller | FAIL with UnauthorizedCaller | Second Moment 6 artifact; proves CPI-only enforcement |
| test_happy_path_end_to_end | PASS | Mint → confirm → disburse → repay, clean |
| test_renewal_cycles_state_correctly | PASS | ACTIVE → RENEWED → ACTIVE; due_ts updates; amendment_hash appended |
| test_state_machine_rejects_invalid_transitions | PASS | All invalid transitions → InvalidStateTransition |
| test_default_creates_auction | PASS | execute_af_default → Auction PDA exists |
| test_vault_share_accounting | PASS | Deposit → withdraw proportional; yield earned shows as share appreciation |
| test_ltv_enforced_at_mint | PASS | LTV over 60% → LTVExceeded |
| test_only_custodian_can_confirm_custody | PASS | Non-custodian signer → UnauthorizedCustodian |
| test_overflow_protection | PASS | Extreme values → MathOverflow, not panic |

Additional coverage at your discretion — what matters is that these ten names exist, produce the expected outcomes, and emit parseable output (stdout with test names clearly delimited, error codes in the failure messages).

The output format. Your test command will be streamed via SSE (§9 below) to the frontend. Standard anchor test output works — the frontend parses ANSI color codes and test-name patterns. Don't pipe through anything that strips colors.

CI. Get a minimum-viable GitHub Actions workflow running anchor test on every push. Green CI by Day 7 at the latest. Red CI blocks the frontend's daily deploy.

## 8. Off-chain backend — event monitor + APIs

You're running a small Node/TS service (or Rust if you prefer) that does three jobs:

Job 1: Chain event monitor. Subscribe to logs from Loan, Vault, TRDC, Auction programs via connection.onLogs(). Parse events (emit them from programs via emit! macros — at minimum: TRDCMinted, CustodyConfirmed, Disbursed, PaymentMade, Renewed, Repaid, Overdue, Defaulted, AuctionCreated, BidPlaced, AuctionClosed). Write to Supabase tables for fast frontend reads. Write failures must not block chain state — the chain is truth; the indexer is read acceleration.

Job 2: API endpoints for off-chain data.

| Endpoint | Purpose |
| --- | --- |
| POST /api/appraisal-requests | Create an appraisal request (frontend Step 1 of loan wizard) |
| GET /api/appraisal-requests/:reqId | Frontend poll for convergence status |
| POST /api/appraisal-submissions | Appraiser submits a valuation |
| GET /api/assets/:reqId/photos | IPFS gateway proxy (avoid CORS in frontend) |
| GET /api/ccb/:hash | Fetch CCB PDF from IPFS by hash |
| POST /api/demo/seed | Seed Devnet demo state (admin-only, demo mode) |
| POST /api/demo/advance/:moment | Execute scripted demo moment (admin-only) |

Auth: wallet signature for user endpoints; pubkey whitelist for admin endpoints.

Job 3: SSE test-runner endpoint.

GET /api/tests/stream

→ text/event-stream

→ spawns `anchor test` child process

→ pipes stdout + stderr as SSE events

→ closes connection on process exit with final event { status: 'done', exitCode: N }

This powers /admin/tests on the frontend. If anchor test against Devnet takes too long (it will — Devnet RPCs are slow), run against solana-test-validator spawned fresh for each run, with the Vaulx programs pre-deployed as a fixture. Target: full test run in under 60 seconds.

Fallback. Record a video of the test run by Day 13 as a static .mp4 asset. If the SSE endpoint fails on demo day, the video plays instead. This fallback is mandatory — Moment 6 is the mission-critical demo close; it cannot fail on camera.

Tech stack. Your choice. Default recommendation: Node + TypeScript + Fastify or Next.js API routes (if you co-locate with frontend). Supabase client. Helius RPC for log subscriptions (more reliable than public Devnet RPC).

## 9. Security — points of attention

These are the things that must not slip. You know all of them; flagging so nothing gets overlooked under deadline pressure:

- CPI caller validation on disburse. Two-layer (signer check + sysvar inspection). This is the whole thesis.

- Signer validation on every write. #[account(signer)] is not enough — check pubkey matches expected authority (custodian for confirm_custody, borrower for borrower actions, multisig for default).

- PDA seeds are not secrets. Don't rely on seed complexity for access control; always check authority explicitly.

- State machine transitions enforced in code, not documentation. Every instruction begins with a require!(current_state in allowed_predecessors, InvalidStateTransition).

- Math overflow. checked_add, checked_mul, checked_div everywhere involving token amounts, timestamps, or interest accrual. Return MathOverflow error; never panic.

- Rent exemption. Every account you create is rent-exempt. Anchor handles this if you use init; manual account creation requires explicit check.

- Account constraints redundancy. Where security-critical, enforce both in #[derive(Accounts)] constraints AND in the instruction body. Defense in depth.

- No UncheckedAccount on security-sensitive accounts. Only for accounts you explicitly validate in the instruction body.

- Close account attacks. If any account is closable, ensure the close authority is correct and the account is marked as closed to prevent reinitialization.

- The fiduciary-alienation hash is legal truth. The CCB PDF hash you store in TRDC metadata is what the SCD partnership relies on for enforceability. Don't compute it server-side; the frontend computes it from the user-signed PDF, and you verify it matches on-chain by receiving it as an instruction argument.

- Upgrade authority. For hackathon: your wallet is fine. For mainnet: Squads 2-of-3. Document the handoff plan in the deploy script.

- Program ID publication. After final Devnet deploy, commit the program IDs to the repo. The frontend bakes them in at build time via env vars.

What's explicitly NOT required for hackathon:

- Formal audit (post-seed)

- Bug bounty program (post-mainnet)

- Fuzz testing beyond what you'd write normally

- Formal verification (mainnet consideration)

## 10. Integration contract with frontend

IDL publication. Commit IDL JSON files to a shared location (suggest: packages/idls/*.json in monorepo, or a separate vaulx-idls repo if infra is split). On every program change, regenerate + commit. Freeze by May 1 (Day 10); changes after that require same-day sync with Claude Code Max.

Events. Emit via emit! macro on every state change. Frontend uses these for live UI updates without needing to poll on-chain state.

Error enum. Publish a single VaulxError enum. Frontend parses error codes for user-friendly messages. Named variants to include:

CustodyNotConfirmed

UnauthorizedCaller

UnauthorizedCustodian

InvalidStateTransition

LTVExceeded

InsufficientVaultLiquidity

MathOverflow

PaymentAmountMismatch

RenewalWindowClosed

AuctionClosed

NotWhitelisted

BidBelowMinimum

KYCRequired

Account layouts. Keep them stable after May 1. Field additions at the end of structs are fine; reordering or renaming is not.

Demo seed API. Expose a demo-seed script the frontend operator can call (or run as a CLI from admin panel) that:

- Mints demo Devnet USDC to 4 preset wallets

- Seeds 4 vaults with initial config

- Creates 3 pre-primed TRDCs in various states (one PENDING_CUSTODY for Moment 3 start, one ACTIVE for Moment 5 repayment, one near-default for Moment 9)

- Returns a JSON manifest of pubkeys for the frontend to display

## 11. Deployment

Network: Devnet only. Submission URL points to Devnet-deployed programs.

Program IDs: generate fresh for Vaulx v1 deployment (don't reuse prior GarantiFi program IDs — clean slate signals fresh codebase to audit readers later). Commit IDs to programs.json at repo root.

Upgrade authority: your wallet for hackathon. Document in DEPLOY.md that mainnet deployment requires Squads 2-of-3 with specified signers (George, Marcelo, Edson).

Rent budget: you'll burn through a few hundred Devnet SOL across test deploys and demo seeding. Get airdrop automation in place Day 1 so you're not hand-faucet-ing at 2am on May 9.

Solana CLI version pinning. Pin anchor version, Solana CLI version, and Rust version in Anchor.toml + rust-toolchain.toml. The frontend team needs reproducible builds; version drift causes IDL mismatches that are hard to debug.

## 12. Build sequence — 18 days synced to frontend

| Days | Deliverable | Synced frontend dependency |
| --- | --- | --- |
| 1–2 (Apr 22–23) | Program skeletons; IDLs with placeholder instructions; first draft VaulxError enum | Frontend Day 1 uses stubbed IDLs |
| 3–4 (Apr 24–25) | TRDC Program complete; Vault Program deposit/withdraw complete; happy-path test passing | Frontend Day 3 generates real client from IDLs |
| 5–6 (Apr 26–27) | Loan Program create_ccb_trdc + confirm_custody + CPI-enforced disburse; the two critical failing tests written and passing-as-failures | Frontend Day 5 builds Borrower Wizard against real chain |
| 7–8 (Apr 28–29) | pay_installment + repay_ccb; event emission on all state changes; indexer writing to Supabase | Frontend Day 7–9 builds Loan Detail + Payment |
| 9–10 (Apr 30–May 1) | Renewal flow complete; IDLs frozen; multisig skeleton (dev bypass flag active) | Frontend IDL consumption lock at May 1 EOD |
| 11–12 (May 2–3) | Auction Program; default flow; demo seed script | Frontend Day 11–12 builds Lender + Auction |
| 13 (May 4) | Test suite complete with all 10 named tests; SSE endpoint live; pre-recorded test-run video produced as fallback | Frontend Day 13 builds Admin panels |
| 14 (May 5) | Full rehearsal with frontend — all 9 moments end-to-end on Devnet | Frontend rehearsal day |
| 15 (May 6) | Fix whatever breaks in rehearsal; polish event emission | Joint polish |
| 16 (May 7) | Production Devnet deploy of final program versions; lock program IDs; hand over manifest to frontend | Frontend deploys to Vercel prod |
| 17 (May 8) | Demo video recording support — operator on-call for chain-side issues | Demo recorded |
| 18 (May 9) | Buffer — submission prep | Submission prep |
| May 10 | Submission |  |

Critical path items (delays cascade):

- IDL freeze May 1 (Day 10). Slipping this slips frontend Week 2 wholesale.

- Two critical failing tests working as failures by Day 6. If these slip, Moment 6 demo artifact is at risk.

- Event emission complete by Day 8. Frontend's live-update UX depends on this; without events, everything polls and feels slow.

- Demo seed script by Day 13. Without it, rehearsal day is a debugging day instead of a recording prep day.

## 13. Open questions for you to flag

- Monorepo vs. split repos? Programs + off-chain backend + frontend in one pnpm workspace, or three separate repos? Recommendation: monorepo for the hackathon (faster IDL + types sharing), split later. Your call — you own the infra choice.

- Indexer tech stack — Node/TS (easier frontend integration), Rust (faster, more aligned with Solana-native patterns), or Anchor's idl-event-parser + serverless? Your call; flag what you're picking by Day 2.

- Civic Pass integration timing. Real SDK wiring or full mock for demo? Recommendation: mock it (feature flag); real integration post-hackathon. Confirm.

- BRZ on Devnet. Is there an existing Devnet BRZ mint or do we deploy a mock SPL token? Mock is fine for demo purposes (Moment 8 just needs the vault variant visible, not a real-liquidity BRL).

- Multisig for defaults. For demo, feature flag bypass is fine. Post-hackathon, decide whether Squads or a custom 2/3 implementation.

- Test validator vs. Devnet for test suite streaming. If Devnet-based anchor test is too slow (>60s), switch to ephemeral solana-test-validator for the SSE endpoint. Decide Day 11.

- CCB PDF generation authority. Frontend generates and computes hash; your program receives hash as argument. Confirm you're OK with this split (vs. generating server-side).

End of BRD. Companion documents: Canonical Spec v3 (product + business), Frontend BRD (UI + UX), this document (backend + on-chain). Any contradictions resolve in favor of the Canonical Spec on product scope, this document on on-chain semantics, and the Frontend BRD on UI behavior.